## Service
Application Modernization
AIPAM-AD-ModernizationAdvisory.CustomerDeck.pptx

## AI-Powered AMA Tooling
Stage | Phase | Service Module | Acticity | Mandatory | Grouped tasks | Responsible | AMA v2.0 Template | AMA v2.0 Tool | Repo in Devops | New Accelerator | AWS Tools | Microsoft Tool | GCP tool
Onboarding​ | Onboarding​ | Kick-off | Project kick-off | Required | Yes | Project Manager | AIPAM-KickOff_2025.pptx | ->OneClick Sense (meetings) |  | ->OneClick Modernization
Onboarding​ | Onboarding​ | Kick-off | Methodology overview | Required | Yes | Project Manager
Onboarding​ | Onboarding​ | Kick-off | Current architecture presentation | Required | Yes | Project Manager
Onboarding​ | Onboarding​ | Kick-off | Application portfolio presentation | Required | Yes | Project Manager
Onboarding​ | Onboarding​ | Management | Funding Program Management | Required | Yes | Project Manager
Onboarding​ | Onboarding​ | Management | Billing hitos Management | Required | Yes | Project Manager
Onboarding​ | Onboarding​ | Management | Coordinate the meeting with Applications and Infrastructure Teams | Required | Yes | Project Manager
Onboarding​ | Onboarding​ | Strategic Alignment Workshop | Business Drivers | Required | Yes | Modernisation Consultant
Onboarding​ | Onboarding​ | Strategic Alignment Workshop | Modernization Drivers Workshop | Optional | Yes | Modernisation Consultant | AIPAM-AD-ApplicationModernizationDrivers.Template.docx | ->Prompt Management |  | ->OneClick Modernization
Onboarding​ | Onboarding​ | Strategic Alignment Workshop | Modernization Drivers Workshop | Optional | Yes | Modernisation Consultant | AIPAM-AD-ApplicationModernizationDrivers.Template.docx | ->OneClick Sense (meetings) |  | ->OneClick Modernization
Onboarding​ | Onboarding​ | Strategic Alignment Workshop | Capacity Map (AS-IS) | Required | No | Modernisation Consultant
Onboarding​ | Onboarding​ | Strategic Alignment Workshop | CAF / WAF | Required | Yes | Infraestructure Consultant | ->SWAAR | ->Prompt Management |  | ->OneClick Modernization
Onboarding​ | Onboarding​ | Strategic Alignment Workshop | Operational Costs | Required | No | Modernisation Consultant
Onboarding​ | Onboarding​ | Strategic Alignment Workshop | Workshop results analysis | Required | Yes | Modernisation Consultant
Onboarding​ | Onboarding​ | Strategic Alignment Workshop | Application Inventory Analysis | Required | Yes | Modernisation Consultant
Onboarding​ | Onboarding​ | Strategic Alignment Workshop | Generate an application discovery and evaluation plan (prioritization) | Required | Yes | Modernisation Consultant
Discovery & Assessment | AI-Powered IT Discovery​ | AI-Powered Application Discovery​
Discovery & Assessment | AI-Powered IT Discovery​ | AI-Powered Application Discovery​ | Discovery & Assessment Plan (prioritized apps, source code, pre-requirements,..) | Required | Yes | Modernisation Consultant
Discovery & Assessment | AI-Powered IT Discovery​ | AI-Powered Application Discovery​ | Application Discovery (Source Code Analysis) | Required | No | Modernisation Consultant |  | ->Prompt Management |  |  | ->GitHub Copilot Migration (Java/.Net) ->AWS Transform (.Net) ->Cast Highlight ->Application Modernization Assessment ->Resilient Application Readiness Assessment ->modelizeIT ->CloudHedge ->AWS Microservice Extractor for .NET ->Porting Assistant for .NET | ->GitHub Copilot Modernization(Generate the report) ->Azure Migrate (App Discovery) ->Azure Dr. Migrate
Discovery & Assessment | AI-Powered IT Discovery​ | AI-Powered Application Discovery​ | Application Discovery (Source Code Analysis) | Required | No | Modernisation Consultant | AIPAM-AD-ApplicationModernization.Migration&ModernizationStrategy.Template.pptx | ->VSCode Agent | ->VSCode Agent |  | ->GitHub Copilot Migration (Java/.Net) ->AWS Transform (.Net) ->Cast Highlight ->Application Modernization Assessment ->Resilient Application Readiness Assessment ->modelizeIT ->CloudHedge ->AWS Microservice Extractor for .NET ->Porting Assistant for .NET | ->GitHub Copilot Modernization(Generate the report) ->Azure Migrate (App Discovery) ->Azure Dr. Migrate
Discovery & Assessment | AI-Powered IT Discovery​ | AI-Powered Application Discovery​ | Application usability and accessibility Discovery | Optional | Yes | Modernisation Consultant
Discovery & Assessment | AI-Powered IT Discovery​ | AI-Powered Application Discovery​ | Application Dependency Mapping | Required | Yes | Modernisation Consultant |  | ->Prompt Management |  |  | ->Cast Imaging ->Cloudamize | Devin
Discovery & Assessment | AI-Powered IT Discovery​ | AI-Powered Application Discovery​ | Application Dependency Mapping | Required | Yes | Modernisation Consultant |  | ->VSCode Agent | ->VSCode Agent
Discovery & Assessment | AI-Powered IT Discovery​ | AI-Powered Application Discovery​ | Application Portfolio Rationalization Matrix | Required | No | Modernisation Consultant | MOA-AMBP-PR-ApplicationTechnicalSurvery(TimeMatrix).xlsx | ->Prompt Management |  | ->OneClick Modernization
Discovery & Assessment | AI-Powered IT Discovery​ | Infrastructure & Network Discovery
Discovery & Assessment | AI-Powered IT Discovery​ | Infrastructure & Network Discovery | Network Flow & Connectivity Analysis | Optional | Yes | Infraestructure Consultant |  |  |  |  | ->Matilda ->Cloudamize | ->Dr. Migrate ->Cloudokit
Discovery & Assessment | AI-Powered IT Discovery​ | Infrastructure & Network Discovery | Security & Compliance Baseline | Optional | Yes | Infraestructure Consultant |  |  |  |  | ->Matilda ->Cloudamize | ->Dr. Migrate ->Cloudokit
Discovery & Assessment | AI-Powered IT Discovery​ | Infrastructure & Network Discovery | Dependency Mapping (Infra-Level) | Optional | Yes | Infraestructure Consultant |  |  |  |  | ->Matilda ->Cloudamize | ->Dr. Migrate ->Cloudokit
Discovery & Assessment | AI-Powered IT Discovery​ | Infrastructure & Network Discovery | Infrastructure Health & Lifecycle Review | Optional | Yes | Infraestructure Consultant |  |  |  |  | ->Matilda ->Cloudamize | ->Dr. Migrate ->Cloudokit
Discovery & Assessment | AI-Powered IT Discovery​ | AI-Powered Database Discovery​
Discovery & Assessment | AI-Powered IT Discovery​ | AI-Powered Database Discovery​ | Database migration tool setup (Client) | Required | No | Modernisation Consultant | 2. AI-Powered Database Assessment​ | ->Prompt Management ->GitHub Copilot |  |  | ->AWS Schema Conversion Tool ->AWS Database Migration Service ->Ora2Pg ->AWS Database Fleet Advisor | ->Azure Database Migration Service (DMS) ->Azure Database for PostgreSQL Migration Service
Discovery & Assessment | AI-Powered IT Discovery​ | AI-Powered Database Discovery​ | Database Migration Tool Execution | Required | Yes | Modernisation Consultant |  | ->Neo4J | Hernan Duque - Scripts Base de datos Relacional
Discovery & Assessment | AI-Powered IT Discovery​ | AI-Powered Database Discovery​ | Database Graph Analysis Tool Execution | Required | Yes | Modernisation Consultant
Discovery & Assessment | AI-Powered IT Discovery​ | AI-Powered Database Discovery​ | Generate report from the database analysis tool | Required | No | Modernisation Consultant
Discovery & Assessment | AI-Powered Assessment | AI-Powered Strategic Analysis
Discovery & Assessment | AI-Powered Assessment | Strategic Modernization Approach | Strategic analysis of applications and databases | Required | Yes | Modernisation Consultant | AIPAM-AD-RefactoringProfiles.Template.xlsx | ->Prompt Management |  | ->OneClick Modernization
Discovery & Assessment | AI-Powered Assessment | Strategic Modernization Approach | Develop an application modernization approach for the applications within scope | Required | Yes | Modernisation Consultant | AIPAM-AD-DatabaseMigrationReport.Template.docx | ->Prompt Management | ->OneClick Knowledge Base (repos) | ->OneClick Modernization
Discovery & Assessment | AI-Powered Assessment | Strategic Modernization Approach | Define the refactoring profile for projects that require refactoring | Required | Yes | Modernisation Consultant | AIPAM-AD-ApplicationModernizationApproach.Template.docx | ->Prompt Management |  | ->OneClick Modernization | ->AWS Migration Hub Strategy Recommendations ->AWS Application Migration Service | ->Azure Advisor ->Azure Migrate (assessment)
Discovery & Assessment | AI-Powered Assessment | Strategic Modernization Approach | Present the application modernization approach to key stakeholders | Required | Yes | Modernisation Consultant
Discovery & Assessment | AI-Powered Assessment | Strategic Modernization Approach | Conduct a Q&A session to define the modernization path for each application | Required | Yes | Modernisation Consultant
Strategic Design | Cloud Application Architecture Definition | Cloud Application Architecture Definition
Strategic Design | Cloud Application Architecture Definition | AI-Guided Cloud Architecture Definition​ | Cloud Architecture Design (Prepare an infrastructure diagram using reference architectures. Prepare a data flow diagram of the infrastructure architecture. Prepare a design of the observability and monitoring for each in-scope application. Present the results of the architecture definition. ) | Required | No | Modernisation Consultant | 4. Cloud Application Architecture Definition​ | ->Prompt Management |  | ->OneClick Modernization |  | ->Azure Architecture Center ->Azure OpenAI (assist)
Strategic Design | Cloud Application Architecture Definition | Landing Zone Alignment | Create Landing Zone Strategy | Optional | Yes | Infraestructure Consultant
Strategic Design | Cloud Application Architecture Definition | Landing Zone Alignment | Landing Zone Strategy Alignment | Optional | Yes | Modernisation Consultant |  | ->Prompt Management |  | ->OneClick Modernization
Strategic Design | Cloud Application Architecture Definition | DevOps Strategy Alignment​ | Create DevOps Strategy | Optional | Yes | Modernisation Consultant | AIPAM-AD-DevOpsDiagnosticCheckList.Template.xlsx | ->Prompt Management |  | ->OneClick Modernization
Strategic Design | Cloud Application Architecture Definition | DevOps Strategy Alignment​ | DevOps Strategy Alignment | Optional | Yes | Modernisation Consultant | AIPAM-AD-DevOps.Template.docx | ->Prompt Management |  | ->OneClick Modernization
Strategic Design | Migration & Modernization Consolidation Plan | Business Case​ & TCO Modeling
Strategic Design | Migration & Modernization Consolidation Plan | Business Case​ & TCO Modeling | Business Case Workshop | Required | Yes | Modernisation Consultant | 5. Business Case & TCO Modeling | ->OneClick Sense (meetings)
Strategic Design | Migration & Modernization Consolidation Plan | Business Case​ & TCO Modeling | Business Case Workshop | Required | Yes | Modernisation Consultant | 5. Business Case & TCO Modeling | ->Prompt Management
Strategic Design | Migration & Modernization Consolidation Plan | Business Case​ & TCO Modeling | Estimate Cloud Cost | Required | No | Modernisation Consultant
Strategic Design | Migration & Modernization Consolidation Plan | Business Case​ & TCO Modeling | Business Case Estimation | Required | No | Modernisation Consultant | 5. Business Case & TCO Modeling | ->Prompt Management | ->OneClick Knowledge Base (repos) | ->OneClick Modernization | ->AWS Pricing Calculator Trusted Advisor | ->Azure TCO Calculator ->Azure Pricing Calculator
Plan | Migration & Modernization Consolidation Plan | Migration & Modernization Consolidation Plan
Plan | Migration & Modernization Consolidation Plan | Migration & Modernization Consolidation Plan | Compilation of migration and modernization strategies | Required | Yes | Modernisation Consultant & Infraestructure Consultant | AIPAM-AD-ApplicationModernization.Migration&ModernizationStrategy.Template.pptx | ->Prompt Management |  | ->OneClick Modernization | ->AWS Migration Hub ->AWS Application Migration Service | ->Azure Migrate (Assessment + Migration)
Plan | Migration & Modernization Consolidation Plan | Migration & Modernization Consolidation Plan | Compilation of business cases | Required | Yes | Modernisation Consultant & Infraestructure Consultant |  | ->OneClick Knowledge Base (repos)
Plan | Migration & Modernization Consolidation Plan | Migration & Modernization Consolidation Plan | Analysis of alternatives and selection of the most optimal strategy to execute the cloud transition | Required | Yes | Modernisation Consultant & Infraestructure Consultant
Plan | Migration & Modernization Consolidation Plan | Migration & Modernization Consolidation Plan | Development of the implementation-phase roadmap | Required | Yes | Modernisation Consultant & Infraestructure Consultant
Plan | Migration & Modernization Consolidation Plan | Migration & Modernization Consolidation Plan | Consolidation of required specialized capabilities | Required | Yes | Modernisation Consultant & Infraestructure Consultant |  | ->OneClick Knowledge Base (repos) |  | ->OneClick Sales
Plan | Migration & Modernization Consolidation Plan | Migration & Modernization Consolidation Plan | Sizing of the effort and projected duration | Required | Yes | Modernisation Consultant & Infraestructure Consultant
Plan | Migration & Modernization Consolidation Plan | Migration & Modernization Consolidation Plan | Executive presentation of the results | Required | Yes | Modernisation Consultant | AIPAM-AD-ApplicationModernization.ClosePresentation.Template.pptx | ->Prompt Management |  | ->OneClick Modernization
Strategic Design | Rapid Modernization PoV | Modernization PoV AI-Assisted (Optional)
Strategic Design | Rapid Modernization PoV | Rapid Modernization PoV | Define the PoV plan. | Optional | Yes | Modernisation Consultant
Strategic Design | Rapid Modernization PoV | Rapid Modernization PoV | Contextualize the modernization strategy, technical design and align objectives with the hyperscaler funding (if the proposal includes it) | Optional | Yes | Solution Engineer | AIPAM-AD-ApplicationModernization.PoC.docx | ->OneClick Generator |  | ->OneClick Modernization
Strategic Design | Rapid Modernization PoV | Rapid Modernization PoV | Set up the environment and prepare test data. | Optional | Yes | Solution Engineer |  | ->OneClick Generator
Strategic Design | Rapid Modernization PoV | Rapid Modernization PoV | Implement and integrate the PoV. | Optional | Yes | Solution Engineer |  | ->OneClick Generator |  |  | ->AWS Migration Hub Refactor Spaces ->AWS Transform for VMWare Mainframe and .NET ->Amazon Elastic VMWare Service ->AWS App2Container ->AWS Schema Conversion Tool ->Cloudamize ->CloudHedge ->AWS Microservice Extractor for .NET ->Porting Assistant for .NET | ->Dr Migrate ->Cloudokit
Strategic Design | Rapid Modernization PoV | Rapid Modernization PoV | Conduct testing, validation, and present results. | Optional | Yes | Solution Engineer |  | ->OneClick Generator
|  | Project management | Follow-up and control |  |  | Project Manager |  | ->OneClick Sense (meetings)
|  | Support | Rationalization Analysis support | Optional |  | XDC Associate
|  | Support | Application Discovery support | Optional |  | XDC Senior Consultant